## Sheet1
S.No | Bug Title | Module Name | Bug Logged By | Assigned to
1 | 1.Intime & Outtime is taken as 1200 ,1300. | ATTENDANCE | MEGHA YADAV
2 | Design of submit and cancel button. | ATTENDANCE | MEGHA YADAV
3 | Design of Description. | ATTENDANCE | MEGHA YADAV
4 | Attendance date is not displayed on the listing page | ATTENDANCE | MEGHA YADAV
5 | Attendance date is displayed as applied date | ATTENDANCE | MEGHA YADAV
6 | User is able to enter the future date for attendance. | ATTENDANCE | MEGHA YADAV
7 | Reject button is not working on the approve attendance at the manager end. | ATTENDANCE | MEGHA YADAV
8 | No limit for description on the attendance form. | ATTENDANCE | MEGHA YADAV
9 | Validation for apply attendance and approval attendance are not displayed. | ATTENDANCE | MEGHA YADAV
10 | Description displayed in the attendance field at the listing of applied attendance. | ATTENDANCE | MEGHA YADAV
11 | Attendance approved for future date from manger end but it is not displayed in the dashboard at the employee end. | ATTENDANCE | MEGHA YADAV
12 | Date format is displayed different at the emp and(01/18/2017) ,listing(18/01/2017) ,manager end(18-01-2017) | ATTENDANCE | MEGHA YADAV
13 | Out-time should not be before In time. | ATTENDANCE | MEGHA YADAV
14 | Alignment and design of separation form | SEPARATION | MEGHA YADAV
15 | Resign date should not be past or future date | SEPARATION | MEGHA YADAV
16 | Name of separation listing should be "view separation" | SEPARATION | MEGHA YADAV
17 | FNFS should be displayed in place of FNF at the FNF aproval,final fnf approvals,view fnf,process fnf & fnf details | SEPARATION | MEGHA YADAV
18 | Date format at the separation form are diff .resign date(02/02/2017) and joining date(01-Jan-2016),listing(02-Feb-2017) | SEPARATION | MEGHA YADAV
19 | when any user save the separation form but it is not forwarded to manager it is displayed as forwarded in place of parked | SEPARATION | MEGHA YADAV
20 | view FNF should not be displayed on the separation view at the rejection. | SEPARATION | MEGHA YADAV
21 | when we dont give any remark for reject/approve it should be displayed as N/A. | SEPARATION | MEGHA YADAV
22 | File name is not displayed,when we upload any document. | TRAVEL | MEGHA YADAV
23 | User is not able to upload any document. | TRAVEL | MEGHA YADAV
24 | Date format is different everywhere. | TRAVEL | MEGHA YADAV
25 | Department name is incorrect at the level1 & level2. | TRAVEL | MEGHA YADAV
26 | Spelling of PROCEED is incorrect at the level1 & level2. | TRAVEL | MEGHA YADAV
27 | Reject button is not clear at the level2. | TRAVEL | MEGHA YADAV
28 | Revert remark should be mandatory. | TRAVEL | MEGHA YADAV
29 | when travel voucher is reverted from level2 it is displayed forwarded at the level1. | TRAVEL | MEGHA YADAV
30 | When travel voucher is approved from level2 , it is still displayed as forwarded at the level1. | TRAVEL | MEGHA YADAV
31 | Employee name should be mandatory in case of advance taken from any employee. | TRAVEL | MEGHA YADAV
32 | Balance amount is not displayed at the level 1 & level2, when user takes advance more than balance amount. | TRAVEL | MEGHA YADAV
33 | Designation id is not displayed at the travel master allowence. | TRAVEL | MEGHA YADAV
34 | Detail of Local Conveyance,Miscellaneous Expense,Detail of Miscellaneous Expense are not mandatory but these field are displayed a validation message. | TRAVEL | MEGHA YADAV
35 | Dropdown functionality is not working properly at the travel master allowence. | TRAVEL | MEGHA YADAV
36
37
38
39
40
41
42
43
44
45
46
47
48