## Sheet1
SCHEDULE 0F FEB 2017-
Date | Megha Yadav | Shivansh Shah
2017-02-01 | Study about swatch | Testing on SWATCH(Whole )
2017-02-02 | KT of swatch from shivansh | Retesting on SWATCH(Whole)
2017-02-03 | study about iffco | Retesting on SWATCH(Whole )
2017-02-04 | study about iffco,testing on iffco | Retesting on SWATCH(Whole)
2017-02-05 | Sunday | Sunday
2017-02-06 | Testing of iffco,HR PORTAL(Maintainence) | Retesting on SWATCH(Whole )
2017-02-07 | Testing of iffco,HR PORTAL(Maintainence) | Testing of iffco
2017-02-08 | Testing of iffco,HR PORTAL(Maintainence) | Testing of iffco
2017-02-09 | Testing of iffco,HR PORTAL(Maintainence) | Testing of iffco
2017-02-10 | Testing of iffco,HR PORTAL(Maintainence) | Testing of iffco , HR Portal (Integration Leave Encashment)
2017-02-11 | Second saturday | Second saturday
2017-02-12 | Sunday | Sunday
2017-02-13 | retesting on iffco ,HR PORTAL(Maintainence) | Re-Testing of iffco,HR Portal (Integration Leave)
2017-02-14 | retesting on iffco ,HR PORTAL(Maintainence) | Re-Testing of iffco,HR Portal (Integration LTA)
2017-02-15 | retesting on iffco ,HR PORTAL(Maintainence) | Re-Testing of iffco,HR Portal (Integration Medical)
2017-02-16 | retesting on iffco ,HR PORTAL(client specific changes) | Re-Testing of iffco,HR Portal (Integration Income Tax)
2017-02-17 | retesting on iffco ,HR PORTAL(client specific changes) | Re-Testing of iffco
2017-02-18 | retesting on iffco ,HR PORTAL(client specific changes) | Re-Testing of iffco
2017-02-19 | Sunday | Sunday
2017-02-20 | Testing Syncing process in iffco, | Testing Syncing process in iffco,
2017-02-21 | Testing Syncing process in iffco, | Testing Syncing process in iffco,
2017-02-22 | Testing on Hypermart(SEO Points) | Testing for changes on Swatch after UAT
2017-02-23 | Testing on Hypermart(SEO Points) | Testing on Hypermart(SEO Points)
2017-02-24 | Testing of Training module of HR Portal | Testing for changes on Swatch after UAT
2017-02-25 | fourth saturday | fourth saturday
2017-02-26 | Sunday | Sunday
2017-02-27 | Testing of Training module of HR Portal | Retesting for changes on Swatch UAT
2017-02-28 | Testing of Training module of HR Portal | Retesting for changes on Swatch UAT
hr portal,swtch ,iffco ,performance of jmeter.
istbq